## Form
Wabash Valley Communications · Worked Example
Risk / Finding Register (POA&M)
Authority |  | Adopted by Wabash Valley Communications under the authority of Anthony Reyes, Director.
Owner |  | Security Coordinator
Version / Dates |  | Version 1.0 Effective Date 2026-06-01 Next Review 2027-06-01
Classification |  | Restricted
Review cadence |  | Reviewed monthly by the Security Coordinator; open items tracked to closure.
Boundary
This register holds findings from assessments, scans, and audits, tracked to closure. Enterprise-level risks are maintained in the Risk Register and cross-referenced in the Risk Register Ref column.
Finding Entries
Finding ID | Source (type + reference) | Finding | Impact Rank | Risk Register Ref | Owner (Role) | Remediation Action | Due Date | Status | Closure Date / Evidence
F-01 | Vulnerability scan 2026-03 (host SRV-02) | Unpatched OS on a CAD application server | High (service) | R-02 | County IT | Apply vendor patch in the maintenance window | 2026-05-15 | Closed | 2026-05-12; change ticket #4471
F-02 | External assessment 2026-02 | MFA not enforced for remote administrative access | High (life-safety) | R-04 | Security Coordinator | Enforce MFA on the VPN and admin accounts | 2026-06-30 | In Progress
F-03 | Vulnerability scan 2026-03 | Legacy SMBv1 enabled on two file shares | Medium (service) | R-06 | County IT | Disable SMBv1; confirm no dependency | 2026-06-15 | In Progress
F-04 | Self-assessment 2026-01 | Logging not centralized; gaps in retention | Medium (data) | R-08 | Security Coordinator | Forward logs to the county log store; set retention | 2026-08-31 | Open
F-05 | External assessment 2026-02 | Visitor sign-in not enforced at the comms room | Low | R-11 | Security Coordinator | Add visitor log and escort rule | 2026-05-30 | Closed | 2026-05-28; log in use
F-06 | Self-assessment 2026-01 | Second-site failover not tested in 12 months | Medium (service-continuity) | R-12 | County IT | Schedule a failover test with the ESInet provider | 2026-07-31 | Open
Status Summary (as of 2026-06-16)
Total findings
Open
In progress
Overdue (open / in progress past due)
Risk accepted
Closed
Source Authority
NENA-STA-040.2-2024: §3.2, §4.3, §5.2
NIST SP 800-53 Rev. 5: CA-5, CA-7, PM-4, RA-7, SI-2
Approval Signatures
Role | Name | Signature | Date
Security Coordinator | (on file) | (on file) | 2026-06-01
Director | Anthony Reyes | Anthony Reyes | 2026-06-01
Revision History
Version | Date | Author | Summary of Change
1.0 | 2026-06-01 | Security Coordinator | Initial issue; findings from the 2026 assessment cycle entered