## Form
Hickory County 911 · Worked Example
Risk / Finding Register (POA&M)
Authority |  | Adopted by Hickory County 911 under the authority of Tracy Holloway, Director.
Owner |  | Director
Version / Dates |  | Version 1.0 Effective Date 2026-06-01 Next Review 2027-06-01
Classification |  | Restricted
Review cadence |  | Reviewed monthly by the Director; open items tracked to closure.
Boundary
This register holds findings from assessments, scans, and audits, tracked to closure. Enterprise-level risks are maintained in the Risk Register and cross-referenced in the Risk Register Ref column.
Finding Entries
Finding ID | Source (type + reference) | Finding | Impact Rank | Risk Register Ref | Owner (Role) | Remediation Action | Due Date | Status | Closure Date / Evidence
F-01 | County IT review 2026-04 | Dispatch workstations missing current OS security patches | High (service) | R-03 | County IT | Enable a monthly patch window with the county IT contact | 2026-06-30 | In Progress
F-02 | Self-assessment 2026-03 | No multifactor on remote access to the CAD vendor portal | High (life-safety) | R-05 | Director | Turn on MFA through the CAD vendor | 2026-07-15 | Open
F-03 | Self-assessment 2026-03 | Single ISP uplink; no failover path for 9-1-1 delivery | Medium (service-continuity) | R-07 | Director | Price a cellular failover circuit for the budget cycle | 2026-09-30 | Open
F-04 | Facility walkthrough 2026-02 | Server closet shared with cleaning supplies; no lock | Low | R-09 | Director | Install a keyed lock; relocate supplies | 2026-05-31 | Closed | 2026-05-22; photo and work order on file
Status Summary (as of 2026-07-01)
Total findings
Open
In progress
Overdue (open / in progress past due)
Risk accepted
Closed
Source Authority
NENA-STA-040.2-2024: §3.2, §4.3, §5.2
NIST SP 800-53 Rev. 5: CA-5, CA-7, PM-4, RA-7, SI-2
Approval Signatures
Role | Name | Signature | Date
Director | Tracy Holloway | Tracy Holloway | 2026-06-01
Revision History
Version | Date | Author | Summary of Change
1.0 | 2026-06-01 | Director | Initial issue; findings from the 2026 assessment cycle entered