## Log
Change Request & Approval Log
Authority |  | Adopted by Wabash Valley Communications under the authority of Anthony Reyes, Director.
Owner |  | IT Support Lead
Version / Dates |  | Version 1 Effective Date 2026-02-09 Next Review 2027-02-09
Classification |  | Internal
Date range / System |  | Covers 2026-01-01 to 2026-02-06. Systems in scope: all.
Change Requests
Change ID | Date Requested | Description | Risk / Impact | Type (standard / normal / emergency) | Approver (Role) | Scheduled Window | Outcome & Verification
CHG-041 | 2026-01-08 | DMZ reverse-proxy config update | Low | Normal | IT Support Lead | 2026-01-10 22:00 | Success
CHG-042 | 2026-01-15 | GIS server OS patch (tested) | Low; tested in pilot | Normal | IT Support Lead | 2026-01-17 22:00 | Success; hash verified
CHG-043 | 2026-01-22 | New VLAN for records unit | Medium | Normal | IT Support Lead / Director | 2026-01-24 22:00 | Success
CHG-044 | 2026-02-01 | Emergency: SBC firmware fix | Medium; call-quality issue | Emergency | On-call authorizer | 2026-02-01 (immediate) | Success; reconciled
CHG-045 | 2026-02-05 | Firewall rule recertification | Low | Standard | IT Support Lead | 2026-02-06 22:00 | Success
Review Summary
5 changes this period; 1 emergency change, reconciled. No out-of-band changes found.
Sign-off
Role | Name | Signature | Date
Reviewed by | Priya Nair | /s/ Priya Nair | 2026-02-09
Approved by | Anthony Reyes | /s/ Anthony Reyes | 2026-02-09
Retention
Retention: 3 years, stored in the agency’s records system per the Document Handling Standard.
Source Authority
NENA-STA-040.2-2024: §4.4, §5.2
NIST SP 800-53 Rev. 5: CM-3, CM-5, CM-9
Revision History
Version | Date | Author | Summary of Change
1 | 2026-02-09 | Priya Nair | Initial adoption