## Register
Tri-River Regional 911 Center · Worked Example
Risk Register
Authority |  | Adopted by Tri-River Regional 911 Center under the authority of Dr. Lisa Park, Executive Director.
Owner |  | Information Security Analyst
Version / Dates |  | Version 1.0 Effective Date 2026-01-20 Next Review 2027-01-20
Classification |  | Restricted
Review cadence |  | Reviewed monthly by the Information Security Analyst; the register grows through all program phases.
Risk Register Entries
Risk ID | Risk Description | Source / Category | Likelihood | Impact | Risk Rating | Treatment Decision | Risk Owner (Role) | Status | Review Date | Cross-Ref (POA&M / Treatment Log)
RISK-001 | Carrier path creates a 911 call-delivery single point of failure | Continuity | Unlikely | Severe | High | Treat: active-active routing validated quarterly | Information Security Analyst | Treating | 2026-06-05 | POA&M-001
RISK-002 | Expanding multimedia ingestion broadens the attack surface | Technical | Possible | Major | High | Treat: sanitize and sandbox file ingestion | Information Security Analyst | Treating | 2026-06-05 | POA&M-002
RISK-003 | Third-party integrations increase supply-chain exposure | Third-party | Possible | Major | High | Treat: vendor security assessments on renewal | IT Director | Open | 2026-06-05 | POA&M-003
RISK-004 | Privileged access sprawl across two centers | Access | Possible | Major | High | Treat: PAM rollout in progress | Information Security Analyst | Treating | 2026-06-05 | POA&M-004
RISK-005 | Alert fatigue in the monitoring program | Operational | Likely | Moderate | High | Treat: tune SIEM thresholds | Information Security Analyst | Treating | 2026-06-05 | POA&M-005
RISK-006 | Insider misuse of CJIS data | Insider | Unlikely | Severe | High | Treat: enhanced logging and periodic access review | Information Security Analyst | Open | 2026-06-05 | POA&M-006
RISK-007 | Legacy integration without current encryption | Technical | Possible | Moderate | Moderate | Accept: scheduled for replacement in FY27 | IT Director | Accepted | 2026-04-05 | Treatment Log RT-007
Summary (as of 2026-04-06)
Total risks
Open
Treating
Accepted
Closed
Past due for review
Scope & Boundary
This register holds enterprise and strategic risks. Assessment findings tracked to closure are recorded in the Risk / Finding Register (POA&M); current treatment state is maintained in the Risk Treatment / Acceptance Decisions Log. Those documents carry the detail; this register references them.
Likelihood, impact, and rating are scored using the scale defined in the Risk Management Methodology Standard: likelihood from Rare to Almost Certain, impact from Negligible to Severe (against service, data, and life safety), combined into a rating of Low, Moderate, High, or Critical.
Downstream Use
This register is the parent risk record. The Risk / Finding Register (POA&M) feeds findings into it, and the Board / Leadership Security Reporting Template rolls it up for leadership.
Source Authority
NENA-STA-040.2-2024: §4.3, §4.3.1
NIST SP 800-53 Rev. 5: CA-5, PM-9, RA-3, RA-7
Approval Signatures
Role | Name | Signature | Date
Executive Director | Dr. Lisa Park | Dr. Lisa Park | 2026-01-20
Information Security Analyst | (on file) | (on file) | 2026-01-20
Revision History
Version | Date | Author | Summary of Change
1.0 | 2026-01-20 | Information Security Analyst | Initial issue