## Register
Wabash Valley Communications · Worked Example
Risk Register
Authority |  | Adopted by Wabash Valley Communications under the authority of Anthony Reyes, Director.
Owner |  | Security Coordinator
Version / Dates |  | Version 1.0 Effective Date 2026-03-02 Next Review 2027-03-02
Classification |  | Restricted
Review cadence |  | Reviewed quarterly by the Security Coordinator; the register grows through all program phases.
Risk Register Entries
Risk ID | Risk Description | Source / Category | Likelihood | Impact | Risk Rating | Treatment Decision | Risk Owner (Role) | Status | Review Date | Cross-Ref (POA&M / Treatment Log)
RISK-001 | Single upstream path creates a 911 call-delivery single point of failure | Continuity | Possible | Severe | High | Treat: dual ESInet path under review | Security Coordinator | Treating | 2026-06-10 | POA&M-001
RISK-002 | Patching backlog across shared county systems | Technical | Likely | Major | High | Treat: align to the county patch cycle | IT Support Lead | Treating | 2026-06-10 | POA&M-002
RISK-003 | Part-time security coordination limits monitoring | Operational | Possible | Moderate | Moderate | Accept: monthly review compensates for now | Director | Accepted | 2026-06-10 | Treatment Log RT-003
RISK-004 | Vendor remote access without multi-factor authentication | Third-party | Possible | Major | High | Treat: MFA required in the SLA | Security Coordinator | Treating | 2026-06-10 | POA&M-004
RISK-005 | Mixed cloud and on-prem data without unified logging | Technical | Possible | Moderate | Moderate | Treat: consolidate logging | IT Support Lead | Open | 2026-06-10 | POA&M-005
RISK-006 | Cyber-incident reporting contact not updated before the deadline | Compliance | Unlikely | Moderate | Low | Treat: calendar reminder set before September 1 | Director | Treating | 2026-04-28 | POA&M-006
Summary (as of 2026-04-29)
Total risks
Open
Treating
Accepted
Closed
Past due for review
Scope & Boundary
This register holds enterprise and strategic risks. Assessment findings tracked to closure are recorded in the Risk / Finding Register (POA&M); current treatment state is maintained in the Risk Treatment / Acceptance Decisions Log. Those documents carry the detail; this register references them.
Likelihood, impact, and rating are scored using the scale defined in the Risk Management Methodology Standard: likelihood from Rare to Almost Certain, impact from Negligible to Severe (against service, data, and life safety), combined into a rating of Low, Moderate, High, or Critical.
Downstream Use
This register is the parent risk record. The Risk / Finding Register (POA&M) feeds findings into it, and the Board / Leadership Security Reporting Template rolls it up for leadership.
Source Authority
NENA-STA-040.2-2024: §4.3, §4.3.1
NIST SP 800-53 Rev. 5: CA-5, PM-9, RA-3, RA-7
Approval Signatures
Role | Name | Signature | Date
Director | Anthony Reyes | Anthony Reyes | 2026-03-02
Security Coordinator | (on file) | (on file) | 2026-03-02
Revision History
Version | Date | Author | Summary of Change
1.0 | 2026-03-02 | Security Coordinator | Initial issue