Board / Leadership Security Reporting Template

Cover Reporting period: Calendar year 2025 Prepared by (role): Director Audience: County board (Sheriff and Commissioners) Owner: Director Classification: Restricted

## 1. Executive Summary

The program completed its first full year. Two High-rated risks remain open: single-carrier 911 routing and an unpatched legacy workstation. The director asks the board to approve funding for a diverse routing option and the workstation replacement. No reportable cyber incidents occurred this period.

## 2. Program Status & Metrics

| Metric | This Period | Trend | Note |
| --- | --- | --- | --- |
| Open risks (by rating) | 5 (3 High) | Flat | Single-carrier 911 routing is the top risk |
| Findings closed this period | 2 | Up | Closed from the POA&M |
| Overdue remediation items | 0 | Flat | All items on schedule |
| Training completion | 100% | Up | 5 of 5 staff completed awareness training |
| Reportable incidents this period | 0 | Flat | No IOT reports required |

## 3. Open Risk Decisions / Items Requiring Leadership Action

| Item | Risk / Finding ref | Decision needed | Recommended action | Owner (role) |
| --- | --- | --- | --- | --- |
| Diverse 911 routing | RISK-001 / POA&M-001 | Approve funding? | Fund a second routing path with the ESInet provider | Director |
| Legacy workstation replacement | RISK-002 / POA&M-002 | Approve purchase? | Replace the unpatched workstation this budget cycle | Director |

## 4. Open Findings Summary

| Finding ref | Severity | Status | Due date | Owner (role) |
| --- | --- | --- | --- | --- |
| POA&M-002 | High | In progress | 2026-05-15 | County IT Administrator |
| POA&M-005 | High | Open | 2026-06-30 | County IT Administrator |

## 5. Reporting Cadence

This report is produced annually for the county board, on the schedule set in the Governance Reporting Calendar. The reporting period and audience are recorded in the cover block above.

## Profile Scaling Notes

| PSAP Profile | Minimum-viable implementation |
| --- | --- |
| Small (1–5 dispatchers, no in-house IT) | One page. The director compiles open risks and overdue items from the registers and reports to the county board annually. Metrics can be counts, not charts. |

Source Authority NENA-STA-040.2-2024: §4.1.1, §4.3 NIST SP 800-53 Rev. 5: PM-4, PM-6, PM-9, PM-15, RA-7

## Sign-off

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Prepared by (Director) | Tracy Holloway | /s/ Tracy Holloway | February 17, 2026 |
| Acknowledged by (Director / leadership) | Tracy Holloway | /s/ Tracy Holloway | February 17, 2026 |

## Revision History

| Version | Date | Author | Summary of Change |
| --- | --- | --- | --- |
| 1.0 | February 17, 2026 | Director | Initial issue |