## Log
Change Request & Approval Log
Authority |  | Adopted by Hickory County 911 under the authority of Tracy Holloway, Director.
Owner |  | County IT Contact
Version / Dates |  | Version 1 Effective Date 2026-02-16 Next Review 2027-02-16
Classification |  | Internal
Date range / System |  | Covers 2026-01-01 to 2026-02-06. Systems in scope: all.
Change Requests
Change ID | Date Requested | Description | Risk / Impact | Type (standard / normal / emergency) | Approver (Role) | Scheduled Window | Outcome & Verification
CHG-014 | 2026-01-12 | Firewall rule cleanup: removed 2 stale rules | Low; no dispatch impact | Normal | County IT Contact | 2026-01-15 22:00 | Success; verified
CHG-015 | 2026-01-20 | CAD server OS security patch | Low; tested first | Normal | County IT / Director | 2026-01-22 22:00 | Success; hash verified
CHG-016 | 2026-02-02 | Emergency: critical VPN gateway patch | Medium; active advisory | Emergency | Director | 2026-02-02 (immediate) | Success; reconciled next day
Review Summary
3 changes this period; 1 emergency change, reconciled the next day. No unapproved changes found.
Sign-off
Role | Name | Signature | Date
Reviewed by | Marcus Reed | /s/ Marcus Reed | 2026-02-16
Approved by | Tracy Holloway | /s/ Tracy Holloway | 2026-02-16
Retention
Retention: 3 years, stored in the agency’s records system per the Document Handling Standard.
Source Authority
NENA-STA-040.2-2024: §4.4, §5.2
NIST SP 800-53 Rev. 5: CM-3, CM-5, CM-9
Revision History
Version | Date | Author | Summary of Change
1 | 2026-02-16 | Marcus Reed | Initial adoption