## Log
Encryption Implementation Verification Records
Authority |  | Adopted by Wabash Valley Communications under the authority of the Wabash Valley Communications Governing Board.
Owner |  | Security Coordinator
Version / Dates |  | Version 1.0 Effective Date February 20, 2026 Next Review August 20, 2026
Classification |  | Restricted / CJIS
Verification cycle / scope |  | Verification cycle: Q1 2026 (as of February 20, 2026). Scope: systems and data categories holding CJI or sensitive data. Verified by (role): Security Coordinator.
Log Entries
Ref # | System / Data Category | Encryption Requirement (at rest / in transit / voice) | Mechanism in Use (algorithm, protocol, key length) | Validation / Test Performed | Date Verified | Result (Compliant / Exception) | Exception & Remediation Date
EV-01 | CAD database | At rest | AES-256 | Config review + scan | 2026-02-20 | Compliant
EV-02 | Dispatch workstations | At rest | AES-256 full-disk | Scan | 2026-02-20 | Compliant
EV-03 | Email transport | In transit | TLS 1.2+ | Config review | 2026-02-20 | Compliant
EV-04 | Backups | At rest | AES-256 | Verified | 2026-02-20 | Compliant
EV-05 | Legacy records app | In transit | TLS 1.0 (legacy) | Scan flagged | 2026-02-20 | Exception | Upgrade to TLS 1.2 by 2026-05-15 (R-2026-031)
Findings
One exception: a legacy records application still negotiates TLS 1.0. Tracked as R-2026-031, upgrade to TLS 1.2 due May 15, 2026. All other systems compliant.
Sign-off
Role | Name | Signature | Date
Reviewed by: Security Coordinator | Dana Mercer | /s/ Dana Mercer | February 20, 2026
Approved by: Executive Director | Anthony Reyes | /s/ Anthony Reyes | February 20, 2026
Retention
Retention: 3 years, stored on the Agency’s secured records share.
Source Authority
NENA-STA-040.2-2024: §6.22, §6.23, §6.23.6
NIST SP 800-53 Rev. 5: CA-7, SC-8, SC-13, SC-28
Indiana statutes and administrative code: 240 IAC 5 (IDACS Security, where IDACS is in scope)
CJIS Security Policy v5.9: §5.10.1.2 (FIPS-validated cryptography for CJI; CJIS-regulated data in scope via IDACS)
Revision History
Version | Date | Author | Summary of Change
1.0 | February 20, 2026 | Security Coordinator | Initial cycle recorded.