## Register
Hickory County 911 · Worked Example
Risk Register
Authority |  | Adopted by Hickory County 911 under the authority of Tracy Holloway, Director.
Owner |  | Director
Version / Dates |  | Version 1.0 Effective Date 2026-02-17 Next Review 2027-02-17
Classification |  | Restricted
Review cadence |  | Reviewed semi-annually by the Director; the register grows through all program phases.
Risk Register Entries
Risk ID | Risk Description | Source / Category | Likelihood | Impact | Risk Rating | Treatment Decision | Risk Owner (Role) | Status | Review Date | Cross-Ref (POA&M / Treatment Log)
RISK-001 | Single upstream carrier creates a 911 call-delivery single point of failure | Continuity | Possible | Severe | High | Treat: pursue a diverse routing option with the ESInet provider | Director | Open | 2026-07-15 | POA&M-001
RISK-002 | Unpatched legacy workstation on the dispatch network | Technical / vulnerability | Likely | Major | High | Treat: isolate and replace on the next budget cycle | County IT Administrator | Treating | 2026-05-15 | POA&M-002
RISK-003 | County IT staffed by one person creates a coverage gap | Operational | Possible | Major | High | Treat: document backup support with county IT and the CAD vendor | Director | Open | 2026-07-15 | POA&M-003
RISK-004 | Limited physical security at the co-located server closet | Physical | Unlikely | Moderate | Moderate | Accept: compensating locks and an access log are in place | Director | Accepted | 2026-07-15 | Treatment Log RT-004
RISK-005 | Vendor remote access without multi-factor authentication | Third-party | Possible | Major | High | Treat: require MFA in the IT support agreement | County IT Administrator | Treating | 2026-04-08 | POA&M-005
Summary (as of 2026-04-09)
Total risks
Open
Treating
Accepted
Closed
Past due for review
Scope & Boundary
This register holds enterprise and strategic risks. Assessment findings tracked to closure are recorded in the Risk / Finding Register (POA&M); current treatment state is maintained in the Risk Treatment / Acceptance Decisions Log. Those documents carry the detail; this register references them.
Likelihood, impact, and rating are scored using the scale defined in the Risk Management Methodology Standard: likelihood from Rare to Almost Certain, impact from Negligible to Severe (against service, data, and life safety), combined into a rating of Low, Moderate, High, or Critical.
Downstream Use
This register is the parent risk record. The Risk / Finding Register (POA&M) feeds findings into it, and the Board / Leadership Security Reporting Template rolls it up for leadership.
Source Authority
NENA-STA-040.2-2024: §4.3, §4.3.1
NIST SP 800-53 Rev. 5: CA-5, PM-9, RA-3, RA-7
Approval Signatures
Role | Name | Signature | Date
Director | Tracy Holloway | Tracy Holloway | 2026-02-17
County IT Administrator | (on file) | (on file) | 2026-02-17
Revision History
Version | Date | Author | Summary of Change
1.0 | 2026-02-17 | Director | Initial issue