## Form
Wabash Valley Communications · Worked Example
Risk Treatment / Acceptance Decisions Log
Authority |  | Adopted by Wabash Valley Communications under the authority of Anthony Reyes, Director.
Owner |  | Security Coordinator
Version / Dates |  | Version 1.0 Effective Date 2026-06-01 Next Review 2027-06-01
Classification |  | Restricted
Coverage |  | Records treatment and acceptance decisions, maintained on a rolling basis by the Security Coordinator. Decision authority for risk acceptances: the Director, on the recommendation of the Security Coordinator.
Decision Entries
Risk ID | Risk | Decision | Rationale | Decision Authority | Decision Date | Re-evaluation Date | Residual Risk Note
R-04 | MFA not enforced for remote admin access | Mitigate | Enforce MFA on the VPN and admin accounts | Security Coordinator | 2026-03-01 | 2027-03-01 | Residual low once enforced
R-08 | Logging not centralized; retention gaps | Mitigate | Forward logs to the county log store and set retention | Security Coordinator | 2026-03-01 | 2027-03-01
R-10 | Legacy CAD add-on cannot support modern TLS | Accept | Vendor end-of-life; replacement scheduled FY27; segmented and monitored | Anthony Reyes, Director | 2026-03-01 | 2026-09-01 | Compensating controls: network segmentation and monitoring until replacement
R-12 | Second-site failover untested in 12 months | Mitigate | Schedule an annual failover test with the ESInet provider | County IT | 2026-03-01 | 2027-03-01
R-14 | Third-party maintenance VPN exposure | Transfer | Covered by the vendor contract SLA and the Agency's cyber insurance | Anthony Reyes, Director | 2026-03-01 | 2027-03-01 | Vendor bears defined liability; access is logged
Currently Accepted Risks
Risk ID | Accepted by (name / role) | Re-evaluation Date | Conditions on acceptance
R-10 | Anthony Reyes, Director | 2026-09-01 | Segmentation and monitoring maintained until the FY27 replacement; revisit if replacement slips
Retention
Retention: retained for the life of each risk plus three years, stored in the Agency's governance records, per the Document Handling Standard.
Source Authority
NENA-STA-040.2-2024: §3.2, §4.3, §5.2
NIST SP 800-53 Rev. 5: PM-9, PM-28, RA-7
Sign-off
Role | Name | Signature | Date
Security Coordinator | (on file) | (on file) | 2026-06-01
Director | Anthony Reyes | Anthony Reyes | 2026-06-01
Revision History
Version | Date | Author | Summary of Change
1.0 | 2026-06-01 | Security Coordinator | Initial issue; decisions from the 2026 risk cycle recorded