## Form
Hickory County 911 · Worked Example
Risk Treatment / Acceptance Decisions Log
Authority |  | Adopted by Hickory County 911 under the authority of Tracy Holloway, Director.
Owner |  | Director
Version / Dates |  | Version 1.0 Effective Date 2026-06-01 Next Review 2027-06-01
Classification |  | Restricted
Coverage |  | Records treatment and acceptance decisions, maintained on a rolling basis by the Director. Decision authority for risk acceptances: the Director.
Decision Entries
Risk ID | Risk | Decision | Rationale | Decision Authority | Decision Date | Re-evaluation Date | Residual Risk Note
R-03 | Dispatch workstations unpatched | Mitigate | Monthly patch window with county IT is low cost | Director | 2026-04-10 | 2027-04-10
R-05 | No MFA on CAD vendor portal | Mitigate | MFA is available at no cost and closes a life-safety exposure | Director | 2026-04-10 | 2027-04-10 | Residual low once enabled
R-07 | Single ISP uplink; no failover | Accept | Cellular failover deferred to the next budget cycle; short-term outage risk tolerated | Tracy Holloway, Director | 2026-04-10 | 2026-10-10 | Accepts a few hours of outage exposure until funded; mutual-aid fallback in place
R-09 | Server closet shared and unlocked | Mitigate | A keyed lock is inexpensive and reduces tamper risk | Director | 2026-02-15 | 2027-02-15 | Residual low after lock installed
Currently Accepted Risks
Risk ID | Accepted by (name / role) | Re-evaluation Date | Conditions on acceptance
R-07 | Tracy Holloway, Director | 2026-10-10 | Pursue a cellular failover circuit at budget; re-evaluate sooner if outages occur
Retention
Retention: retained for the life of each risk plus three years, stored in the Agency's governance records, per the Document Handling Standard.
Source Authority
NENA-STA-040.2-2024: §3.2, §4.3, §5.2
NIST SP 800-53 Rev. 5: PM-9, PM-28, RA-7
Sign-off
Role | Name | Signature | Date
Director | Tracy Holloway | Tracy Holloway | 2026-06-01
Revision History
Version | Date | Author | Summary of Change
1.0 | 2026-06-01 | Director | Initial issue; decisions from the 2026 risk cycle recorded