## Patch Schedule
Patch Management Schedule & Tracking Log
Authority |  | Adopted by Tri-River Regional 911 Center under the authority of Dr. Lisa Park, Director.
Owner |  | Information Security Analyst
Version / Dates |  | Version 1 Effective Date 2026-01-26 Next Review 2027-01-26
Classification |  | Restricted
Patch Schedule
System Type / Criticality | Patch Source & Test Requirement | Frequency | Owner (Role) | Next Due | Status
CAD (Critical, redundant) | Vendor; test environment | Monthly; critical within 72h | Information Security Analyst | 2026-03-01 | Due soon
Integrations GIS/RMS/ALI (Critical) | Vendor; test environment | Monthly | Information Security Analyst | 2026-03-01 | Due soon
Servers (Critical) | Patch tool; staged | Monthly | IT team | 2026-03-01 | Due soon
Workstations (Standard) | Patch tool | Monthly | IT team | 2026-02-20 | Overdue
Network / SBC (Critical) | Vendor firmware; test first | Quarterly | Information Security Analyst | 2026-04-01 | On track
DNS software (Critical) | Vendor; test first | Monthly | Information Security Analyst | 2026-03-01 | Due soon
Summary (as of 2026-03-01)
Patch cadences tracked
Overdue (flagged)
Past due by date
Escalation for Missed Items
When a scheduled patch cycle is missed or a critical patch is overdue, the Information Security Analyst is notified within 24 hours and the update is prioritized for the next window.
Source Authority
NENA-STA-040.2-2024: §5.5, §6.4
NIST SP 800-53 Rev. 5: CM-3, MA-2, SI-2
Approval
Role | Name | Signature | Date
Information Security Analyst | Raymond Osei | /s/ Raymond Osei | 2026-01-26
Director | Dr. Lisa Park | /s/ Dr. Lisa Park | 2026-01-26
Revision History
Version | Date | Author | Summary of Change
1 | 2026-01-26 | Raymond Osei | Initial adoption

## Patch Tracking Log
Patch Tracking Log
Date Applied | System / Asset ID | Patch / Update | Criticality | Approver (Role) | Outcome
2026-02-02 | CAD (Center A/B) | OS rollup 2026-02 | Critical | Information Security Analyst | Staged, tested, deployed
2026-02-02 | GIS/RMS/ALI | Integration updates | Critical | Information Security Analyst | Staged, tested, deployed
2026-02-03 | Servers (fleet) | Patch cycle 2026-02 | Critical | IT team | Deployed, monitored
2026-02-04 | Workstations (x38) | Monthly updates | Standard | IT team | Deployed, success
2026-02-08 | Edge (zero-day) | Emergency patch | Critical | Emergency-change authority | Tested, deployed, reconciled 12h