## Form
Tri-River Regional 911 Center · Worked Example
Risk / Finding Register (POA&M)
Authority |  | Adopted by Tri-River Regional 911 Center under the authority of Dr. Lisa Park, Director.
Owner |  | Information Security Analyst
Version / Dates |  | Version 1.0 Effective Date 2026-06-01 Next Review 2027-06-01
Classification |  | Restricted
Review cadence |  | Reviewed monthly by the Information Security Analyst; open items tracked to closure.
Boundary
This register holds findings from assessments, scans, and audits, tracked to closure. Enterprise-level risks are maintained in the Risk Register and cross-referenced in the Risk Register Ref column.
Finding Entries
Finding ID | Source (type + reference) | Finding | Impact Rank | Risk Register Ref | Owner (Role) | Remediation Action | Due Date | Status | Closure Date / Evidence
F-01 | SIEM alert review 2026-04 | Disabled endpoint agent on three workstations | High (service) | R-01 | IT Director | Reinstall and monitor agent coverage in the SIEM | 2026-05-20 | Closed | 2026-05-18; SIEM coverage report
F-02 | Quarterly scan 2026-03 | Critical CVE on a GIS integration server | High (service) | R-03 | IT Director | Patch and revalidate the GIS feed | 2026-05-31 | Closed | 2026-05-29; scan re-run clean
F-03 | External assessment 2026-02 | Privileged accounts without periodic recertification | High (data) | R-05 | Information Security Analyst | Stand up quarterly privileged-access recertification | 2026-07-15 | In Progress
F-04 | Quarterly scan 2026-03 | TLS 1.0 still accepted on one internal service | Medium (data) | R-07 | IT Director | Disable TLS 1.0/1.1 on the service | 2026-06-30 | In Progress
F-05 | Tabletop 2026-02 | Backup call-handling runbook out of date | High (life-safety) | R-02 | Information Security Analyst | Revise and re-exercise the continuity runbook | 2026-06-15 | In Progress
F-06 | SIEM alert review 2026-04 | Excessive failed logins not alerting to on-call | Medium (service) | R-09 | Information Security Analyst | Tune SIEM rule and on-call escalation | 2026-05-25 | Closed | 2026-05-24; rule and page test on file
F-07 | Risk review 2026-01 | Single fiber path between the two centers | Medium (service-continuity) | R-13 | IT Director | Accepted for this cycle; tracked in the decisions log | 2026-07-01 | Risk Accepted | 2026-04-02; see decisions log
Status Summary (as of 2026-06-16)
Total findings
Open
In progress
Overdue (open / in progress past due)
Risk accepted
Closed
Source Authority
NENA-STA-040.2-2024: §3.2, §4.3, §5.2
NIST SP 800-53 Rev. 5: CA-5, CA-7, PM-4, RA-7, SI-2
Approval Signatures
Role | Name | Signature | Date
Information Security Analyst | (on file) | (on file) | 2026-06-01
Director | Dr. Lisa Park | Dr. Lisa Park | 2026-06-01
Revision History
Version | Date | Author | Summary of Change
1.0 | 2026-06-01 | Information Security Analyst | Initial issue; findings from the 2026 assessment cycle entered