Server Room / Equipment Area Hardening Assessment Record

Cover Assessment date: February 17, 2026 Assessor (role): Director Scope: the Agency's server rooms and equipment areas, including cabling, equipment, and displays. Assessment period: Annual, February 2026 Owner: Director Classification: Restricted

## 1. Executive Summary

The Hickory County 911 equipment area is the communications room shared with the Sheriff's Office. Placement, cabling, and equipment locking meet the standard. The open gap is display protection: two dispatch screens are visible from the shared corridor, and the PSAP rack sits in the same room as Sheriff network gear. Privacy filters, a shorter auto-lock, and a separate lockable rack are in progress.

## 2. Hardening Requirements Conformance

| Requirement area | What good looks like | Conformance | Notes / gap |
| --- | --- | --- | --- |
| Placement | Sensitive systems in restricted, climate-controlled rooms matched to classification | Conforms | Shared comms room is access-controlled and climate-controlled |
| Cabling & conduit | Locked, labeled, restricted-zone cabling; inspected for tampering | Conforms | Cabling in a locked tray, labeled |
| Equipment locking | Equipment in locked racks or cabinets; keys limited to authorized staff | Gap | PSAP rack shares the room with Sheriff gear; no separate lock yet |
| Display protection | Privacy filters and automatic screen lock on dispatch and call-taker displays | Gap | Two screens visible from the shared corridor |

## 3. Findings

| ID | Finding | Severity | Recommendation |
| --- | --- | --- | --- |
| F-01 | Two dispatch screens are visible from the shared Sheriff's Office corridor | Med | Add privacy filters and reduce auto-lock to 5 minutes |
| F-02 | PSAP server rack is not separately locked within the shared room | Low | Install a lockable rack for PSAP equipment |

## 4. Remediation Tracking

| Finding ID | Owner (role) | Action | Due date | Status |
| --- | --- | --- | --- | --- |
| F-01 | Director | Fit privacy filters and set auto-lock | March 31, 2026 | In progress |
| F-02 | Director | Install a lockable rack | June 30, 2026 | Open |

## 5. Shared-Space / Co-location Risk

| Co-located equipment | Shared with | Risk | Compensating control |
| --- | --- | --- | --- |
| PSAP server rack and switch | Hickory County Sheriff's Office | Sheriff IT staff have physical proximity to PSAP equipment | PSAP equipment moving to a separate lockable rack; access logged |
| Dispatch workstations | Sheriff's Office staff in the shared room | Screens viewable by non-PSAP staff | Privacy filters and a 5-minute auto-lock |

## Profile Scaling Notes

| PSAP Profile | Minimum-viable implementation |
| --- | --- |
| Small (1–5 dispatchers, no in-house IT) | The director walks the equipment room once a year with the hardening standard in hand, notes any gap, and records a compensating control where a shared space cannot be fixed. The assessment is short and on paper. |

Source Authority List only the authorities that map to content in this artifact. Group by authority; order sections and control IDs numerically. No padding. Replace the lines below with the citations that actually apply. NENA-STA-040.2-2024: §5.2, §6.1.1, §6.1.4, §6.1.5, §6.7.2 NIST SP 800-53 Rev. 5: CA-2, PE-3, PE-4, PE-5, PE-14, PE-18

## Sign-off

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Assessor (Director) | Tracy Holloway | /s/ Tracy Holloway | February 17, 2026 |
| Reviewed by (Director) | Tracy Holloway | /s/ Tracy Holloway | February 17, 2026 |

## Revision History

| Version | Date | Author | Summary of Change |
| --- | --- | --- | --- |
| 1.0 | February 17, 2026 | Director | Initial assessment |